## Data Dictionary
Lab 7 — Stakeholder Analysis, Resistance Management and Change Leadership
Certified Lean Six Sigma Black Belt (CLSSBB) Training · TGS-2024051900 · Version v4
About this workbook
Twelve named stakeholders on this project — map their influence and support, and plan the specific action that moves each one.
This workbook is a TEMPLATE. The blank columns are the ones you complete during the lab.
Sheets in this workbook
Sheet | What it contains | Rows
StakeholderMap | Be honest about current support. A map that says everyone is supportive is wrong. | 12
RACI | One A per row. Never two. | 10
ResistanceLog | Resistance is data. Log the real objection, not the polite one. | 6
Column definitions
Sheet | Column | Definition / unit
StakeholderMap | Stakeholder
StakeholderMap | Role
StakeholderMap | Influence_1to5
StakeholderMap | CurrentSupport | Opposed/Neutral/Supportive/Champion
StakeholderMap | RequiredSupport
StakeholderMap | WhatTheyCareAbout
StakeholderMap | Gap | YOU assess
StakeholderMap | SpecificAction | YOU plan
StakeholderMap | By when
RACI | Deliverable
RACI | BlackBelt
RACI | Sponsor
RACI | ProcessOwner
RACI | Finance
RACI | Quality
RACI | Operators
ResistanceLog | Who
ResistanceLog | StatedObjection
ResistanceLog | UnderlyingConcern
ResistanceLog | Type | Technical / Political / Cultural
ResistanceLog | Response
Specification limits used throughout this course
Project Y | Seal weld burst pressure
Unit | kPa
Lower spec limit (LSL) | 180
Target | 220
Upper spec limit (USL) | 260

## StakeholderMap
Be honest about current support. A map that says everyone is supportive is wrong.
Stakeholder | Role | Influence_1to5 | CurrentSupport | RequiredSupport | WhatTheyCareAbout | Gap | SpecificAction | By when
VP Operations | Project sponsor |  | Champion
Suzhou Plant Manager | Owns the worst-performing plant |  | Opposed
Singapore Plant Manager | Owns the reference plant |  | Supportive
Penang Plant Manager | Process owner |  | Neutral
Quality Director | Regulatory accountability |  | Supportive
Manufacturing Engineering Lead | Owns the fixture design |  | Opposed
Night shift supervisor, Suzhou | Runs the worst-performing cell |  | Opposed
Finance Controller | Signs off the benefit |  | Neutral
Supplier Quality Manager | Owns the seal ring supplier |  | Neutral
Line operators (x22) | Do the work |  | Neutral
Maintenance Manager | Must add the interlock |  | Neutral
Regulatory Affairs | Approves any process change |  | Supportive

## RACI
One A per row. Never two.
Deliverable | BlackBelt | Sponsor | ProcessOwner | Finance | Quality | Operators
Project charter
Data collection plan
MSA study
Baseline capability
Root cause validation
DOE execution
Pilot approval
Control plan
Benefit validation
Handover to process owner

## ResistanceLog
Resistance is data. Log the real objection, not the polite one.
Who | StatedObjection | UnderlyingConcern | Type | Response