## Data Dictionary
Lab 1 — Select and Charter Your Capstone Project
Certified Lean Six Sigma Black Belt (CLSSBB) Training · TGS-2024051900 · Version v4
About this workbook
A project selection matrix pre-loaded with six candidate projects, and a blank charter form.
This workbook is a TEMPLATE. The blank columns are the ones you complete during the lab.
Sheets in this workbook
Sheet | What it contains | Rows
SelectionMatrix | Six candidates the sponsor put forward. Score, weight and rank them. | 6
COPQ | Annualised Cost of Poor Quality for the project you select. | 7
Charter | The project charter. Every field is mandatory. | 16
Column definitions
Sheet | Column | Definition / unit
SelectionMatrix | Candidate
SelectionMatrix | StatedAs | Problem or Solution? — check this FIRST
SelectionMatrix | StrategicFit_1to5
SelectionMatrix | AnnualBenefit_SGD
SelectionMatrix | DataAvailability_1to5
SelectionMatrix | ScopeManageability_1to5
SelectionMatrix | SponsorCommitment_1to5
SelectionMatrix | TechnicalRisk_1to5
SelectionMatrix | WeightedScore | YOU compute
SelectionMatrix | Accept/Reject
SelectionMatrix | RejectionReason
COPQ | CostElement
COPQ | BasisOfEstimate
COPQ | Annualised_SGD
Charter | Element
Charter | YourEntry
Specification limits used throughout this course
Project Y | Seal weld burst pressure
Unit | kPa
Lower spec limit (LSL) | 180
Target | 220
Upper spec limit (USL) | 260

## SelectionMatrix
Six candidates the sponsor put forward. Score, weight and rank them.
Candidate | StatedAs | StrategicFit_1to5 | AnnualBenefit_SGD | DataAvailability_1to5 | ScopeManageability_1to5 | SponsorCommitment_1to5 | TechnicalRisk_1to5 | WeightedScore | Accept/Reject | RejectionReason
Reduce seal weld leak defects on infusion pumps | Problem
Deploy a new MES across all three plants | Solution
Improve OTIF for hospital distributor orders | Problem
Reduce warranty returns on occlusion sensors | Problem
Cut inspection overtime in Suzhou | Problem
Buy a second burst-test rig | Solution

## COPQ
Annualised Cost of Poor Quality for the project you select.
CostElement | BasisOfEstimate | Annualised_SGD
Scrap
Rework labour
Warranty
Expedited freight
Lost margin
Capacity consumed
TOTAL

## Charter
The project charter. Every field is mandatory.
Element | YourEntry
Business case
Problem statement (4-part test: process / period / gap / impact)
Goal statement (SMART)
Scope — IN
Scope — OUT
Preliminary Y
Baseline performance
Target performance
Team members
Sponsor
Milestone — Define
Milestone — Measure
Milestone — Analyze
Milestone — Improve
Milestone — Control
Expected annual benefit (SGD)